PROGRESS REPORT

NUS-ISS  ·  Architecting AI Systems Practice Module

| Field | Details |
| --- | --- |
| Project Title | WriteAgent — Multi-Agent AI Novel Writing System |
| Date of Report | 9 April 2026 (End of Week 1, Day 1–7) |
| Report Name | Team X_09Apr2026 |
| Team Members | M1: zt (Lead/Arch) · M2: [Name] (Agent Dev) · M3: [Name] (Consistency/RAI) · M4: [Name] (Memory/Backend) · M5: [Name] (Frontend/MLSecOps) |
| Submission Period | Day 1–7 ¦ Next Report Due: 22 April 2026 (Day 14) |

# 1.  Summary of Work Done

The following tasks were completed during Week 1 (Days 1–7, 9–15 April 2026).

## 1.1  Project Kickoff & Requirements Analysis

- Conducted a team kickoff meeting to review the NUS-ISS AAS Practice Module briefing and align on project scope, deliverables, and success criteria.

- Analysed all nine required deliverables (architecture document, agent design doc, RAI report, AI security risk register, MLSecOps pipeline, source code, testing artifacts, UI prototype, presentation) and mapped each to specific implementation tasks.

- Selected WriteAgent — a multi-agent AI novel writing system — as the group project. The system produces narrative prose scene-by-scene using a pipeline of specialised AI agents coordinated through a LangGraph StateGraph.

- Tech Stack Decision:  Finalised the technology stack:

- LLM: Alibaba Qwen (via DashScope API, OpenAI-compatible) — cost-effective, strong multilingual support

- Agent Orchestration: LangGraph (StateGraph with conditional edges)

- Vector Store / Memory: ChromaDB (persistent, local embedding)

- Backend: FastAPI + uvicorn + WebSocket

- Frontend: Vanilla JS + D3.js (single-page, no build step)

- Testing: pytest (unit + integration)

- DevOps: Docker + Docker Compose + GitHub Actions

## 1.2  System Architecture Design

- Designed the logical architecture: 5-agent pipeline (WorldbuildingAgent → CharacterAgent → PlotAgent → ConsistencyChecker → NarrativeOutputAgent) with a conditional branch to NegotiationSubgraph on contradiction detection.

- Defined GraphState TypedDict as the shared data contract between all nodes — includes novel metadata, agent outputs, memory context, contradiction results, negotiation log, and audit fields.

- Designed the physical architecture: single-host Docker Compose setup with separate containers for FastAPI service, ChromaDB persistence volume, and Nginx reverse proxy.

- Produced high-level data flow diagram showing request lifecycle: User → FastAPI → background thread → LangGraph graph → ChromaDB read/write → WebSocket push → Frontend.

## 1.3  Agent Roles & Module Assignment

- Defined the responsibility boundary for each of the 5 agents and assigned ownership to team members.

- Agreed on BaseAgent abstract class contract: all agents expose run(state: GraphState) → dict, with _call_llm() and _parse_json() provided by the base.

- Designed the three-tier memory strategy (hot = sliding window, warm = ChromaDB semantic retrieval, cold = absolute world rules) and agreed on token-budget enforcement algorithm.

- Agreed on the dual-layer entity attribute model: code-extracted core_attributes (permanent, never overwritten) and LLM-extracted extended_attributes (genre-specific, also permanent after first write).

## 1.4  Planning & Documentation

- Produced a 40-day project roadmap (see Appendix A) with three phases, two fortnightly milestones, and per-member task assignments.

- Set up the Git repository with agreed folder structure: agents/, graph/, memory/, api/, guardrails/, prompts/, utils/, config/, ui/, tests/.

- Created initial .env.example, requirements.txt skeleton, and README outline.

- Each member completed individual research on their assigned domain (see Section 2).

# 2.  Effort Expended

Hours recorded by each team member for Days 1–7 (9–15 April 2026).

| Member & Role | Tasks Performed | Hours |
| --- | --- | --- |
| M1 — zt (Lead / Architect) | Project kickoff & requirements mapping (4h) Logical + physical architecture design (6h) Tech stack decision doc (2h) Team coordination & task assignment (2h) | 14 |
| M2 — [Name] (Agent Developer) | LangGraph & StateGraph study (4h) Agent design pattern research (4h) Prompt engineering patterns review (4h) | 12 |
| M3 — [Name] (Consistency / RAI) | Consistency detection algorithm research (4h) IMDA Model AI Governance Framework review (4h) RAI & bias detection approaches survey (3h) | 11 |
| M4 — [Name] (Memory / Backend) | ChromaDB architecture & embedding strategy study (5h) FastAPI project structure planning (3h) Three-tier memory design research (3h) | 11 |
| M5 — [Name] (Frontend / MLSecOps) | UI/UX wireframe drafting (4h) MLSecOps & LLMSecOps pipeline survey (4h) CI/CD tooling research (GitHub Actions, Docker) (3h) | 11 |
|  | Total | 59 |

# 3.  Problems Encountered

## 3.1  LLM API Selection & Cost Management

- The team evaluated three LLM providers (OpenAI GPT-4o, Anthropic Claude, Alibaba Qwen) for the backend. While GPT-4o and Claude offer superior English prose quality, their per-token costs make extended novel generation expensive. Qwen was selected for its cost-efficiency and strong Chinese language support, but the team is uncertain whether this satisfies assessors expecting a more widely-known model. Clarification from lecturers on LLM choice flexibility would be helpful.

## 3.2  ChromaDB Multilingual Embedding

- ChromaDB's default embedding model (all-MiniLM) is English-optimised. For a Chinese/English bilingual novel system, the semantic retrieval quality for Chinese entity descriptions may be lower than expected. The team is researching multilingual embedding alternatives (e.g., paraphrase-multilingual-MiniLM) but is uncertain about deployment overhead. Guidance on acceptable embedding quality trade-offs would be appreciated.

## 3.3  Scope of "Agent Tool Use" Requirement

- The briefing (Slide 11) requires agents to demonstrate autonomy through "tool use". Our current design has agents calling an LLM and reading/writing ChromaDB — it is unclear whether these count as formal tool use in the assessors' view, or whether OpenAI-style function-calling / MCP tool integration is expected. This affects agent design significantly. Clarification is requested.

# 4.  Plan for the Next 2 Weeks  (Days 8–14, 16–22 April 2026)

Phase 1 completion: implement core infrastructure, BaseAgent, LLM client, and first three agents.

| Days | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Day 8–9 | FastAPI project scaffold + LangGraph StateGraph skeleton + ChromaDB init | M1, M4 | Running API skeleton |
| Day 9–10 | BaseAgent abstract class + LLM client (retry, rate-limit) + token counter + audit logger | M1, M4 | base_agent.py, llm_client.py |
| Day 10–11 | Prompt registry: YAML v1 loader, version-switch API | M1 | prompts/registry.py + 5 YAML files |
| Day 11–12 | WorldbuildingAgent + CharacterAgent: LLM calls, JSON parsing, state output | M2 | worldbuilding_agent.py, character_agent.py |
| Day 12–13 | PlotAgent + human_injection support; initial graph_builder (linear 3-node flow) | M2, M3 | plot_agent.py, graph_builder.py |
| Day 13–14 | GraphState full schema + edges.py; initial unit tests for BaseAgent & LLM client | M1, M4 | state.py, edges.py, test_base.py |
| Day 14 | Progress Report 1 consolidation, review & submission | All | Progress Report 1 |

# Appendix A — 40-Day Project Roadmap

Three phases aligned with fortnightly progress report submissions. Dates assume project start 9 April 2026.

| Milestone | Task / Deliverable | Days | Date (2026) | Owner(s) |
| --- | --- | --- | --- | --- |
| PHASE 1 | Foundation & Infrastructure Setup | Day 1–14 | Apr 9 | All |
| Day 1–2 | Project kickoff: requirements analysis, tech stack finalisation, repo setup, assign modules | Day 1–2 | Apr 9–10 | All (2h meeting + individual) |
| Day 3–4 | System architecture design: logical + physical diagrams, LangGraph flow, GraphState contract | Day 3–4 | Apr 11–12 | M1, M2 |
| Day 5–6 | Infrastructure scaffold: FastAPI skeleton, LangGraph setup, ChromaDB init, project structure | Day 5–6 | Apr 13–14 | M1, M4 |
| Day 7–8 | BaseAgent abstract class, LLM client (retry/rate-limit), token counter, audit logger | Day 7–8 | Apr 15–16 | M1, M4 |
| Day 9–10 | WorldbuildingAgent + CharacterAgent (first 2 agents, LLM calls, prompt YAML v1) | Day 9–10 | Apr 17–18 | M2 |
| Day 11–12 | PlotAgent + human_injection support; basic graph_builder wiring (linear flow) | Day 11–12 | Apr 19–20 | M2, M3 |
| Day 13 | Prompt registry (YAML versioning, hot-swap); .env / settings (Pydantic) | Day 13 | Apr 21 | M1 |
| ★ R1 | Progress Report 1 submission | Day 14 | Apr 22 | All |
| PHASE 2 | Core Agent Features & Memory System | Day 15–28 | Apr 23 | All |
| Day 15–17 | ConsistencyChecker: code pre-scan (regex, proximity detection) + LLM semantic check + fallback merge | Day 15–17 | Apr 23–25 | M3 |
| Day 18–19 | NegotiationSubgraph: multi-round inter-agent dialogue, max-round guard, unresolved logging | Day 18–19 | Apr 26–27 | M3 |
| Day 20–21 | Memory schemas (EntityDoc / SceneArchiveDoc / WorldRuleDoc) + ChromaDB CRUD (entity_store) | Day 20–21 | Apr 28–29 | M4 |
| Day 22–23 | Three-tier retrieval (hot/warm/cold + token budget enforcement); attribute extractor (regex + LLM) | Day 22–23 | Apr 30 – May 1 | M4 |
| Day 24–25 | NarrativeOutputAgent (draft+correction merge); write-permission control; scene archive commit | Day 24–25 | May 2–3 | M2, M4 |
| Day 26–27 | Guardrails: input_sanitizer (prompt injection patterns), content_filter (tiered output filter) | Day 26–27 | May 4–5 | M3 |
| Day 28 | API routes: novel.py (start/scene/inject), entities.py, admin.py, audit.py; WebSocket manager | Day 28 | May 6 | M4, M5 |
| ★ R2 | Progress Report 2 submission | Day 28 | May 6 | All |
| PHASE 3 | Explainability, Security, MLSecOps & Final Deliverables | Day 29–40 | May 7 | All |
| Day 29–30 | UI prototype: Writer tab, World Graph (D3), Conflicts tab, Audit tab; WebSocket real-time events | Day 29–30 | May 7–8 | M5 |
| Day 31–32 | Process Tab (Explainability UI): agent reasoning timeline per scene; /scene/{n}/process API | Day 31–32 | May 9–10 | M3, M5 |
| Day 33 | BiasReviewAgent: bias_report field in GraphState; IMDA-aligned Responsible AI report | Day 33 | May 11 | M3 |
| Day 34 | AI Security Risk Register document (prompt injection, hallucination, adversarial, mitigation table) | Day 34 | May 12 | M1, M3 |
| Day 35 | MLSecOps pipeline: Dockerfile + docker-compose; GitHub Actions CI/CD; monitoring design | Day 35 | May 13 | M5 |
| Day 36 | AI security tests: adversarial inputs, prompt injection scenarios; expand test_guardrails.py | Day 36 | May 14 | M3, M4 |
| Day 37 | Full test suite: unit (5 modules) + integration (API end-to-end) + AI security; coverage report | Day 37 | May 15 | M2, M4 |
| Day 38 | Group project report (all 9 sections) + individual reports writing | Day 38 | May 16 | All |
| Day 39 | Presentation slides (system overview, demo walkthrough, design decisions, RAI, security) | Day 39 | May 17 | M1, M5 |
| ★ Final | Final submission + Progress Report 3 | Day 40 | May 18 | All |

## Sign-off

Submitted by Team X on behalf of all members.

Team Lead Signature: ___________________________          Date: ________________